## 3. Databases
DatabaseID | ServerID (link to Tab 2) |  | Database Name | SQL Version (reported) | State | Size (MB) | Last Backup | mdf | ldf | Environment | Criticality | Application / Functional Owner | Business Purpose | Usage Status | Source Systems | Source Owner | Dependent Systems / Consumers | Dependency Owner | Integration / Processing | Assessment Status | Preliminary Disposition | Assessment Confidence | Discovery Source | Open Questions / Next Action | Notes | RTO / RPO Required | Maximum Downtime / Cutover Window | Operating Window / Peak Period | Data Classification / Regulatory Scope | Retention Requirement | Performance / Growth Baseline | Technical Compatibility Constraints | Preliminary Conclusion
DB-063 | SRV-015 | BB-VV-BD-001 | BB_DATA | SQL Server 2019 | ONLINE | 459280 | 7/14/2026 3:42 | D:\Program Files\Microsoft SQL Server\MSSQL15.MSSQLSERVER\MSSQL\DATA\BB_DATA.mdf | E:\Program Files\Microsoft SQL Server\MSSQL15.MSSQLSERVER\MSSQL\Data\BB_DATA_log.ldf | Production | High | Eric | Supports management reports and dashboards; approximately 90% of the identified outputs still depend on BB_DATA and have not moved to DW. | Active | Jack Henry, BFBNAPDB, DW, IBKR | Eric | Management reports ¦ Dashboards | Eric | SSIS Packages que se conectan con JH (DB2 / ODBC) para alimentar la BD Desde BB_DATA hacia JH con Inyeccion process | In Progress | TBD | High | SQL Server Inspection | Validate upstream source systems and source owners. ¦ Confirm the replacement timeline and all remaining consumers before retirement or cutover. ¦ Capture RTO/RPO, cutover constraints, and the business acceptance owner. | Meeting on 2026-07-22 with Eric and Yanniel: BB-VV-BD-001 / BB_DATA is being replaced or decommissioned (diciembre 2026). All remaining workloads must be migrated to DW before shutdown. Preliminary disposition rationale: Retire only after all remaining reports and dashboards are migrated to DW. Es una base de datos analítica | RTO = 24 hours / RPO = NA | 24 hours | During de injection process (1 AM to 6 AM) | Datos personales. Datos bancarios. Información de cuentas o transacciones. Datos de tarjetas. Información regulatoria. Información confidencial interna. | Retain for 10 years | CPU media y máxima. Memoria utilizada. IOPS. Throughput. Latencia. Conexiones concurrentes. Volumen de transacciones. Duración de procesos batch. Crecimiento mensual o anual. Tamaño proyectado. | SQL Agent ¦ Linked Servers ¦ SSIS ¦ Windows Authentication Cross-database queries ¦ Database Mail CLR ¦ Local disk dependency
DB-013 | SRV-026 | BFBNAPDB | BCP_Global_IBKR_prod | SQL Server 2016 | ONLINE | 400 | 7/14/2026 3:51 | I:\SQL Databases\BCP_Global_IBKR_prod.mdf | F:\SQL Logs\BCP_Global_IBKR_prod_log.ldf | Production | Medium | Yanniel / Eric / Juan Grass | Loads BCP Global / IBKR investment account, balance, customer, and investment data for Brazil reporting and verification. | Active | BCP Global / IBKR API | BCP Global ¦ Bradesco Invest US | VRS/BR9 reports ¦ BI reporting ¦ Bradesco Brazil | BI / Reporting ¦ Bradesco Brazil | API | Pending Validation | TBD | High | Technical Owner Interview | Complete technical validation when controlled access or a validated technical extract becomes available. ¦ Confirm the target disposition after the functional and technical gaps are closed. | The API updates local tables with external accounts, account participants, balance history, and customer-change history. It runs once or twice per day. The main technical complexity is the API connection and update logic. Preliminary disposition rationale: Active API-driven workload; validate downstream consumers and API migration complexity. Se actualiza una vez por dia, por la mañana, cuando corre el proceso que trae la info de BCP Global. El resto del dia se usa para generar reportes Technical Owner de la API: Juan Grass API tiene drivers de SQL Server Reportes de BI, no críticos, Power BI (Juan Grass va a confirmar con el equipo de BI, Ricardo) Node.js utiliza "mssql": "^7.2.1" 4 tablas (cuentas, balances, etc.) | RTO: 4 hours ¦ RPO: 24 hours | Up to 4 hours (preliminary) ¦ Preferred cutover window: After 11:00 AM ET or during a weekend; avoid the 08:00–10:00 AM ET processing window | Daily operating window: approximately 08:00–10:00 AM ET ¦ Peak period: 08:00–10:00 AM ET ¦ API load starts around 08:00, VR files are generated around 09:00, and possible internal/Power BI reporting occurs around 10:00 ¦ Low or no usage expected after the morning window (report schedule pending validation) | Sensitive / Confidential (preliminary) ¦ Customer PII, account-holder information and historical account balances | Historical account balances and processed customer records are retained for business reporting and calculation purposes ¦ Formal retention period, archival, legal-hold and deletion requirements are not defined; pending Business / Compliance validation | Low usage / low data volume ¦ One daily API load and punctual reporting reads ¦ Low concurrency ¦ Growth and infrastructure metrics pending validation | SQL Server-specific Node.js driver, raw SQL queries and connection pooling; no ORM ¦ Cross-engine migration requires driver/query changes and testing ¦ Four main tables identified ¦ Reporting and additional SQL Server dependencies pending validation
Note on K1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on M1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on N1: Concise English description of the business process or capability supported by the database. Detailed technical context remains in Notes. v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on O1: Preliminary usage classification based on interviews, documentation, and available technical evidence. It is not a substitute for activity-log validation. v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on R1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on S1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on T1: Technologies or processing mechanisms explicitly mentioned in the source material. Multiple values are separated with ¦.
Note on U1: Status of the assessment work, separate from the recommended disposition. v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on V1: Preliminary direction only. TBD means the available evidence is not yet sufficient for a target decision.
Note on W1: Derived from evidence source and field completeness: High, Medium, or Low. It does not represent business criticality. v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on X1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on Y1: Actionable validation backlog generated from documented gaps. It does not assert facts not present in the source material.
Note on Z1: Supporting context, interview findings, exceptions, and preliminary disposition rationale.
Note on AA1: Business requirement that must be confirmed with the business/application owner. Suggested format: RTO: 4 hours ¦ RPO: 15 minutes. Do not infer from Criticality, backups, or Usage Status.
Note on AB1: Maximum acceptable service interruption and approved migration window. Suggested format: Max downtime: 2 hours ¦ Window: Saturday 22:00-02:00 ET.
Note on AC1: Business operating hours and periods when migration or downtime should be avoided. Example: Business days 08:00-18:00 ET ¦ Month-end critical.
Note on AD1: Confirmed data sensitivity and regulatory scope. Example: Confidential ¦ Customer PII ¦ GLBA ¦ PCI. Confirm with Security, Compliance, or the Data Owner.
Note on AE1: Required retention, archival, legal-hold, and deletion rules. Example: 7 years online + 3 years archive. Do not infer from current backup history.
Note on AF1: Measured or owner-provided workload baseline. Include CPU, memory, IOPS/throughput, concurrency, batch duration, current size, and growth where available.
Note on AG1: Confirmed technical features or dependencies that may constrain AWS target selection. Example: SQL Agent ¦ Linked Servers ¦ SSIS ¦ Windows Authentication ¦ File Shares. v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on AH1: v15 update: selected values for Caddiel-owned/JHA-supported databases were populated from Bradesco_Databases_Caddiel_Campos_Technical_Owners_v1- Update.xlsx, modified 2026-08-06. Group-level statements remain subject to individual database validation.
Note on V2: Preliminary rationale: Retire only after all remaining reports and dashboards are migrated to DW.
Note on V3: Preliminary rationale: Active API-driven workload; validate downstream consumers and API migration complexity.