## Metrics
Metric | Value
Discovery Phase | 80% |  | 80+
Assessment Phase | 25% |  | 20+
Target-State Definition | 18% |  | 0+
Roadmap Development | 5% |  | 0+
Final Reporting | 0% |  | 0+
Overall Program Completion Estimate | 25% |  | 20+
Area | Assessment | Completion %
Assessment Methodology Defined | Yes | 85%
Deliverable Templates Defined | Yes | 95%
Current-State Analysis Populated | Limited | 20%
Evidence Register | Not Visible | 5%
Maturity Scores | Not Populated | 0%
Governance Findings | Not Populated | 10%
Risk Register | Not Populated | 10%
Target-State Architecture | Conceptual Only | 25%
Remediation Roadmap | Template Only | 10%
Bradesco-Specific Recommendations | Limited | 10%

## WBSdetail
WBS ID | Work Package | Deliverable | Completion %
1 | Project Governance & Engagement Management | Program Oversight | 85%
1.1 | Project Initiation | Kickoff & Alignment | 100%
1.1.1 | Kickoff Meeting | Kickoff Materials | 100%
1.1.2 | Stakeholder Register | Stakeholder Inventory | 90%
1.1.3 | Assessment Methodology | Assessment Framework | 90%
1.1.4 | Communication Plan | Communication Model | 90%
2 | Current State Data Governance Assessment | Current State Assessment | 25%
2.1 | Governance Operating Model Assessment | Governance Assessment | 20%
2.1.1 | Executive Sponsorship Assessment | Sponsorship Analysis | 20%
2.1.2 | Decision Rights Assessment | Decision Matrix | 15%
2.1.3 | Stewardship Assessment | Stewardship Model Assessment | 15%
2.1.4 | Ownership Assessment | Ownership Matrix | 10%
2.2 | Data Domain Assessment | Domain Inventory | 10%
2.2.1 | Customer Domain | Domain Assessment | 5%
2.2.2 | Deposit Domain | Domain Assessment | 5%
2.2.3 | Time Deposit Domain | Domain Assessment | 25%
2.2.4 | Treasury Domain | Domain Assessment | 0%
2.2.5 | Finance Domain | Domain Assessment | 0%
2.2.6 | Regulatory Reporting Domain | Domain Assessment | 0%
2.2.7 | Risk Domain | Domain Assessment | 0%
2.3 | Data Asset Assessment | Data Asset Inventory | 35%
2.3.1 | Source System Inventory | Source Catalog | 30%
2.3.2 | Product Inventory Review | Business Asset Inventory | 50%
2.3.3 | Business Glossary Seed | Glossary Foundations | 20%
3 | Metadata & Catalog Assessment | Metadata Assessment Report | 15%
3.1 | Business Metadata Assessment | Metadata Findings | 20%
3.1.1 | Glossary Assessment | Glossary Gap Analysis | 20%
3.1.2 | Definition Standardization | Standard Definitions | 10%
3.2 | Technical Metadata Assessment | Catalog Findings | 10%
3.2.1 | Catalog Coverage Assessment | Coverage Report | 10%
4 | Data Lineage Assessment | Lineage Assessment | 10%
4.1 | Enterprise Lineage Review | Lineage Inventory | 10%
4.1.1 | Source-to-Landing Review | Lineage Mapping | 10%
4.1.2 | Landing-to-Warehouse Review | Lineage Mapping | 10%
4.1.3 | Warehouse-to-Reporting Review | Lineage Mapping | 5%
4.1.4 | Regulatory Traceability Review | Traceability Matrix | 0%
5 | Data Quality Assessment | DQ Assessment Report | 10%
5.1 | Data Quality Framework Review | DQ Framework Assessment | 15%
5.1.1 | Completeness Assessment | DQ Findings | 10%
5.1.2 | Accuracy Assessment | DQ Findings | 10%
5.1.3 | Consistency Assessment | DQ Findings | 10%
5.1.4 | Timeliness Assessment | DQ Findings | 10%
5.1.5 | Validity Assessment | DQ Findings | 10%
5.2 | Critical Data Elements Program | CDE Framework | 10%
5.2.1 | CDE Inventory | CDE Catalog | 5%
5.2.2 | CDE Ownership | Ownership Assignments | 5%
5.2.3 | CDE Rule Definition | Quality Rule Catalog | 5%
6 | Security, Privacy & Compliance Assessment | Compliance Assessment | 15%
6.1 | Data Classification Assessment | Classification Model | 20%
6.1.1 | Public Classification Review | Classification Standards | 15%
6.1.2 | Internal Classification Review | Classification Standards | 15%
6.1.3 | Confidential Classification Review | Classification Standards | 15%
6.1.4 | Restricted Classification Review | Classification Standards | 15%
6.2 | Regulatory Controls Assessment | Compliance Mapping | 10%
7 | Current State Maturity Assessment | Maturity Scorecard | 0%
7.1 | Strategy & Vision | Maturity Scoring | 0%
7.2 | Policies & Standards | Maturity Scoring | 0%
7.3 | Organization & Roles | Maturity Scoring | 0%
7.4 | Metadata & Catalog | Maturity Scoring | 0%
7.5 | Data Lineage | Maturity Scoring | 0%
7.6 | Data Quality | Maturity Scoring | 0%
7.7 | Classification & Privacy | Maturity Scoring | 0%
7.8 | Retention & Records | Maturity Scoring | 0%
7.9 | Architecture & Platform | Maturity Scoring | 0%
7.1 | Monitoring & Reporting | Maturity Scoring | 0%
8 | Gap Analysis | Enterprise Gap Matrix | 0%
8.1 | Governance Gaps | Gap Assessment | 0%
8.2 | Technology Gaps | Gap Assessment | 0%
8.3 | Organizational Gaps | Gap Assessment | 0%
8.4 | Metadata Gaps | Gap Assessment | 0%
8.5 | Lineage Gaps | Gap Assessment | 0%
8.6 | Data Quality Gaps | Gap Assessment | 0%
9 | Target State Governance Framework | Governance Operating Model | 15%
9.1 | Governance Vision | Vision Statement | 20%
9.2 | Governance Council Design | Governance Charter | 15%
9.3 | Stewardship Model Design | Stewardship Framework | 15%
9.4 | RACI Development | Responsibility Matrix | 15%
9.5 | Escalation Framework | Escalation Model | 10%
9.6 | Decision Rights Framework | Decision Matrix | 15%
10 | Target State Data Architecture | Target Architecture Package | 20%
10.1 | Enterprise Domain Model | Domain Architecture | 10%
10.2 | Governance Architecture | Governance Architecture | 20%
10.2.1 | Unity Catalog Architecture | UC Architecture | 20%
10.2.2 | Metadata Architecture | Metadata Architecture | 15%
10.2.3 | DQ Architecture | DQ Architecture | 15%
10.2.4 | Lineage Architecture | Lineage Architecture | 15%
10.2.5 | Security Architecture | Security Architecture | 15%
10.3 | Medallion Architecture Design | Reference Architecture | 25%
11 | Prioritized Remediation Roadmap | Roadmap Package | 5%
11.1 | Quick Wins (0-90 Days) | Quick Win Plan | 5%
11.2 | Foundation Initiatives (3-6 Months) | Initiative Portfolio | 0%
11.3 | Governance Program (6-12 Months) | Program Roadmap | 0%
11.4 | Enterprise Expansion (12-24 Months) | Strategic Roadmap | 0%
12 | Executive Readout & Closure | Final Assessment Package | 0%
12.1 | Executive Findings | Executive Summary | 0%
12.2 | Risk Assessment | Risk Register | 0%
12.3 | Strategic Recommendations | Recommendation Package | 0%
12.4 | Investment Roadmap | Investment Plan | 0%
12.5 | Final Report Package | Final Deliverables | 0%

## WBS
1_Project Governance & Engagement Management | 1.1_Project Initiation | 1.1.1_Kickoff Meeting
1_Project Governance & Engagement Management | 1.1_Project Initiation | 1.1.2_Stakeholder Register
1_Project Governance & Engagement Management | 1.1_Project Initiation | 1.1.3_Assessment Methodology
1_Project Governance & Engagement Management | 1.1_Project Initiation | 1.1.4_Communication Plan
2_Current State Data Governance Assessment | 2.1_Governance Operating Model Assessment | 2.1.1_Executive Sponsorship Assessment
2_Current State Data Governance Assessment | 2.1_Governance Operating Model Assessment | 2.1.2_Decision Rights Assessment
2_Current State Data Governance Assessment | 2.1_Governance Operating Model Assessment | 2.1.3_Stewardship Assessment
2_Current State Data Governance Assessment | 2.1_Governance Operating Model Assessment | 2.1.4_Ownership Assessment
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.1_Customer Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.2_Deposit Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.3_Time Deposit Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.4_Treasury Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.5_Finance Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.6_Regulatory Reporting Domain
2_Current State Data Governance Assessment | 2.2_Data Domain Assessment | 2.2.7_Risk Domain
2_Current State Data Governance Assessment | 2.3_Data Asset Assessment | 2.3.1_Source System Inventory
2_Current State Data Governance Assessment | 2.3_Data Asset Assessment | 2.3.2_Product Inventory Review
2_Current State Data Governance Assessment | 2.3_Data Asset Assessment | 2.3.3_Business Glossary Seed
3_Metadata & Catalog Assessment | 3.1_Business Metadata Assessment | 3.1.1_Glossary Assessment
3_Metadata & Catalog Assessment | 3.1_Business Metadata Assessment | 3.1.2_Definition Standardization
3_Metadata & Catalog Assessment | 3.2_Technical Metadata Assessment | 3.2.1_Catalog Coverage Assessment
4_Data Lineage Assessment | 4.1_Enterprise Lineage Review | 4.1.1_Source-to-Landing Review
4_Data Lineage Assessment | 4.1_Enterprise Lineage Review | 4.1.2_Landing-to-Warehouse Review
4_Data Lineage Assessment | 4.1_Enterprise Lineage Review | 4.1.3_Warehouse-to-Reporting Review
4_Data Lineage Assessment | 4.1_Enterprise Lineage Review | 4.1.4_Regulatory Traceability Review
5_Data Quality Assessment | 5.1_Data Quality Framework Review | 5.1.1_Completeness Assessment
5_Data Quality Assessment | 5.1_Data Quality Framework Review | 5.1.2_Accuracy Assessment
5_Data Quality Assessment | 5.1_Data Quality Framework Review | 5.1.3_Consistency Assessment
5_Data Quality Assessment | 5.1_Data Quality Framework Review | 5.1.4_Timeliness Assessment
5_Data Quality Assessment | 5.1_Data Quality Framework Review | 5.1.5_Validity Assessment
5_Data Quality Assessment | 5.2_Critical Data Elements Program | 5.2.1_CDE Inventory
5_Data Quality Assessment | 5.2_Critical Data Elements Program | 5.2.2_CDE Ownership
5_Data Quality Assessment | 5.2_Critical Data Elements Program | 5.2.3_CDE Rule Definition
6_SecurityPrivacy_AndComplianceAssessment | 6.1_Data Classification Assessment | 6.1.1_Public Classification Review
6_SecurityPrivacy_AndComplianceAssessment | 6.1_Data Classification Assessment | 6.1.2_Internal Classification Review
6_SecurityPrivacy_AndComplianceAssessment | 6.1_Data Classification Assessment | 6.1.3_Confidential Classification Review
6_SecurityPrivacy_AndComplianceAssessment | 6.1_Data Classification Assessment | 6.1.4_Restricted Classification Review
6_SecurityPrivacy_AndComplianceAssessment | 6.2_Regulatory Controls Assessment | 6.1.1_TBD
7_Current State Maturity Assessment | 7.1_Strategy & Vision | 7.1.1_TBD
7_Current State Maturity Assessment | 7.2_Policies & Standards | 7.2.1_TBD
7_Current State Maturity Assessment | 7.3_Organization & Roles | 7.3.1_TBD
7_Current State Maturity Assessment | 7.4_Metadata & Catalog | 7.4.1_TBD
7_Current State Maturity Assessment | 7.5_Data Lineage | 7.5.1_TBD
7_Current State Maturity Assessment | 7.6_Data Quality | 7.6.1_TBD
7_Current State Maturity Assessment | 7.7_Classification & Privacy | 7.7.1_TBD
7_Current State Maturity Assessment | 7.8_Retention & Records | 7.8.1_TBD
7_Current State Maturity Assessment | 7.9_Architecture & Platform | 7.9.1_TBD
7_Current State Maturity Assessment | 7.10_Monitoring & Reporting | 7.10.1_TBD
8_Gap Analysis | 8.1_Governance Gaps | 8.1.1_TBD
8_Gap Analysis | 8.2_Technology Gaps | 8.2.1_TBD
8_Gap Analysis | 8.3_Organizational Gaps | 8.3.1_TBD
8_Gap Analysis | 8.4_Metadata Gaps | 8.4.1_TBD
8_Gap Analysis | 8.5_Lineage Gaps | 8.5.1_TBD
8_Gap Analysis | 8.6_Data Quality Gaps | 8.6.1_TBD
9_Target State Governance Framework | 9.1_Governance Vision | 9.1.1_TBD
9_Target State Governance Framework | 9.2_Governance Council Design | 9.2.1_TBD
9_Target State Governance Framework | 9.3_Stewardship Model Design | 9.3.1_TBD
9_Target State Governance Framework | 9.4_RACI Development | 9.4.1_TBD
9_Target State Governance Framework | 9.5_Escalation Framework | 9.5.1_TBD
9_Target State Governance Framework | 9.6_Decision Rights Framework | 9.6.1_TBD
10_Target State Data Architecture | 10.1_Enterprise Domain Model | 10.1.1_TBD
10_Target State Data Architecture | 10.2_Governance Architecture | 10.2.1_Unity Catalog Architecture
10_Target State Data Architecture | 10.2_Governance Architecture | 10.2.2_Metadata Architecture
10_Target State Data Architecture | 10.2_Governance Architecture | 10.2.3_DQ Architecture
10_Target State Data Architecture | 10.2_Governance Architecture | 10.2.4_Lineage Architecture
10_Target State Data Architecture | 10.2_Governance Architecture | 10.2.5_Security Architecture
10_Target State Data Architecture | 10.3_Medallion Architecture Design | 10.3.1_TBD