## WBS & Timeline
10-WEEK BRADESCO BANK DATA GOVERNANCE ASSESSMENT - PROJECT PLAN & WBS
Work Breakdown Structure with Gantt Timeline
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
WBS # | Phase / Task | Owner | Deliverable | Status | 13-17 July | 17-24 July | 27-31 July | 3-7 Aug | 10-14 Aug | 17-21 Aug | 24-28 Aug | 31 Aug - 4 Sep | 7-11 Sep | 14-18 Sep
1.0 | PHASE 1: PROJECT INITIATION & PLANNING
1.1 | Kickoff meeting & stakeholder alignment | RSM Team | Kickoff deck & minutes | Complete | Week 1: 2026-07-16
1.2 | Define assessment scope & objectives | RSM Team | Scope statement | Complete | bar: Week 1
1.3 | Identify key stakeholders & SMEs | RSM Team | Stakeholder register | Complete | bar: Week 1
1.4 | Develop detailed project schedule | RSM Team | Project schedule | In Progress | bar: Week 1 to Week 3
1.5 | Establish communication plan | RSM Team | - | Complete | bar: Week 1
1.6 | Set up collaboration tools & data room | RSM Team | Shared workspace | Complete | bar: Week 1
1.7 | Develop data request list | RSM Team | Data request document | Complete | bar: Week 1
2.0 | PHASE 2: Confirm Current State & Define Data Goverannce
2.1 | Conduct stakeholder interviews - Executive Sponsorship, Strategy & In-Flight Initiatives | RSM & Bradesco Team | Interview notes | Complete | Week 2: 2026-07-21
2.2 | Conduct stakeholder interviews - Data Architecture, Platform, Lineage & Metadata | RSM & Bradesco Team | Interview notes | Complete | Week 2: 2026-07-22
2.3 | Conduct stakeholder interviews - Data Quality, CDEs & Regulatory Reporting | RSM & Bradesco Team | Interview notes | In Progress | Week 2: 2026-07-23
2.4 | Distribute & collect surveys/questionnaires | RSM & Bradesco Team | - | Complete | bar: Week 2 to Week 4
2.5 | Collect exisiting documents and policies | Bradesco Team | Document inventory | In Progress | bar: Week 1 to Week 4
2.6 | Review existing documentation & policies | RSM Team | Document inventory | In Progress | bar: Week 2 to Week 4
2.8 | Docutment current-state and assess maturity | RSM Team | - | Not Started | bar: Week 3 to Week 5
2.9 | Review and Confirm Current State Maturity | RSM & Bradesco Team | Deliverbale: Current State Maturity Assessment | Pending Scheduling | Week 5: 2026-08-12
2.10 | Build Sample DG Policy Draft - including DG domains, R&R, Decision making structure & escalation paths | RSM Team | Sample Data Governance (DG) Policy Draft | Not Started | bar: Week 4 to Week 5
2.11 | Review Sample DG Policy Draft | RSM & Bradesco Team | Deliverable: Sample Data Governance Policy Draft | Pending Scheduling | Week 6: 2026-08-18
3.0 | PHASE 3: Review Target State Architecture and conduct Gap Analysis
3.1 | Develop Target State Data Governance | RSM & Bradesco Team | - | Pending Scheduling | Week 5: 2026-08-11
3.2 | Gap analysis (Current State / Policy Draft--> Target State DG ) | RSM Team | Gap analysis matrix | Not Started | bar: Week 5 to Week 6
3.3 | Develop Conceptual Target State DG Architecture | RSM Team | Conceptual Target State DG Architecture | Not Started | bar: Week 6
3.4 | Risk & issue identification | RSM Team | Risk register | Not Started | bar: Week 6
3.5 | Review and validate findings | RSM & Bradesco Team | Deliverbale: Target State DG Architecture, Gap Analysis Matrix, Risk Register | Pending Scheduling | Week 7: 2026-08-26
4.0 | PHASE 4: Recommendations & Roadmap
4.1 | Develop strategic recommendations | RSM Team | - | Not Started | bar: Week 7 to Week 8
4.2 | Prioritize initiatives (effort vs. impact) with estimated investment ranges | RSM Team | - | Not Started | bar: Week 7 to Week 8
4.3 | Define quick wins vs. long-term initiatives | RSM Team | - | Not Started | bar: Week 7 to Week 8
4.4 | Build implementation roadmap | RSM Team | Priortized Implementation Roadmap | Not Started | bar: Week 8
4.5 | Build 30/60/90 day plan | RSM Team | 30/60/90 Day Action Plan | Not Started | bar: Week 8
4.6 | Review Reccomendations and Roadmap | RSM Team / Bradesco Team | Deliverbale: Priortized Implementation Roadmap & 30/60/90 Day Action Plan | Pending Scheduling | Week 9: 2026-09-08
5.0 | PHASE 5: Final Readout & Handoff
5.1 | Draft final assessment report | RSM Team | Draft report | Not Started | bar: Week 9
5.2 | Prepare executive presentation | RSM Team | Executive Presentation | Not Started | bar: Week 9 to Week 10
5.3 | Feedback from client on executive presentation | Bradesco Team | Executive Presentation | Not Started | Week 10: 2026-09-14
5.4 | Deliver final presentation to stakeholders | RSM Team / Bradesco Team | Deliverbale: Executive Presentation | Pending Scheduling | Week 10: 2026-09-17
5.5 | Hand off all deliverables & data and close project | RSM Team / Bradesco Team | Deliverable package | Pending Scheduling | Week 10: 2026-09-18
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Request Target State DG Arch from Bradesco

## Milestones
KEY MILESTONES
# | Milestone | Phase | Target Date | Owner | Dependency
M1 | Current State Maturity Assessment | 2 | 2026-08-12 | RSM & Bradesco Team | Interviews & data complete
M2 | Sample Data Governance Policy Draft | 2 | 2026-08-18 | RSM & Bradesco Team | Current state validated
M3 | Target State DG Architecture, Gap Analysis Matrix, Risk Register | 3 | 2026-08-26 | RSM & Bradesco Team | Policy draft reviewed
M4 | Prioritized Implementation Roadmap & 30/60/90 Day Action Plan | 4 | 2026-09-08 | RSM Team / Bradesco Team | Findings validated
M5 | Executive Presentation | 5 | 2026-09-17 | RSM Team / Bradesco Team | Roadmap approved
M6 | Deliverable package & project close | 5 | 2026-09-18 | RSM Team / Bradesco Team | Final presentation delivered